## 15May to 14 June
Service Level Agreement
Invoice Number |  | Month | May-Aug | Year | 2017-2018
Resource Name | Ritu Sharma,kushal chauhan | Work Order No | F4.3 (145)/RISL/TECH/15/6029 dated 28 Oct 2016 | Work Order Date | 2018-08-14
Sr.No. | Task Assigned | Assigned Date | Assign Task Completion Date | Actual Task Completion Date | Difference*
1 | FMDSS Help Desk Mail Reply | 2018-05-15 | 2018-05-17 | 2018-05-17 | 0
2 | Create Nursery Report With Hindi Format | 2018-05-19 | 2018-05-19 | 2018-05-19 | 0
3 | Performed testing on production. | 2018-05-23 | 2018-05-23 | 2018-05-23 | 0
1 | Implement Changes for Production Server | 2018-06-01 | 2018-06-01 | 2018-06-01 | 0
2 | Help Desk Reply | 2018-06-07 | 2018-06-11 | 2018-06-11 | 0
3 | Fixed Nursery issue in Nursery Module | 2018-06-20 | 2018-06-20 | 2018-06-20 | 0
4 | Mapped New (sikar) Users in Enchorochment Module | 2018-06-26 | 2018-06-26 | 2018-06-26 | 0
1 | Help Desk query resolve for refund | 2018-07-09 | 2018-07-09 | 2018-07-09 | 0
2 | Mapping of Naka as per client requirement | 2018-07-13 | 2018-07-13 | 2018-07-13 | 0
3 | Help Desk Query resolved | 2018-07-16 | 2018-07-16 | 2018-07-16 | 0
4 | Testing of Mobile application(Animal Rescue) | 2018-07-31 | 2018-07-31 | 2018-07-31 | 0
1 | Resolve the issue of Online Ticket booking | 2018-08-03 | 2018-08-03 | 2018-08-03 | 0
2 | Reolve query regarding refund | 2018-08-07 | 2018-08-07 | 2018-08-07 | 0
3 | Map user of depot in pre-production server. | 2018-08-10 | 2018-08-10 | 2018-08-10 | 0

## June-Aug18 (hidden)
Service Level Agreement
Invoice Number |  | Month | Mar-May | Year | 2018
Resource Name | Ritu Sharma, | Work Order No | F4.3 (145)/RISL/TECH/15/6029 dt 28 Oct 2016 | Work Order Date | 2018-07-16
Sr.No. | Task Assigned | Assigned Date | Assign Task Completion Date | Actual Task Completion Date | Difference*
1 | Help Desk Reply | 2018-06-01 | 2018-06-01 | 2018-06-01 | 0
2 | Working on Purchase Dept User in Nursery Module | 2018-06-04 | 2018-06-06 | 2018-06-05 | 1
3 | Add File Uploaded in Nursery Dept User Module and change SP | 2018-06-06 | 2018-06-06 | 2018-06-06 | 0
4 | Fixed Nursery issue in Nursery Module | 2018-06-07 | 2018-06-07 | 2018-06-07 | 0
5 | Created UI for VFMC Registration page | 2018-06-07 | 2018-06-11 | 2018-06-08 | 3
5 | Help Desk Reply | 2018-06-07 | 2018-06-07 | 2018-06-07 | 0 | 0
6 | Create Nursery Purchase history Report for Citizen Users | 2018-06-07 | 2018-06-07 | 2018-06-07 | 0
7 | Add Filter in nursery module | 2018-06-07 | 2018-06-07 | 2018-06-07 | 0
8 | Change Link for Nursery In-charge Counter booking citizen to Development Module | 2018-06-08 | 2018-06-08 | 2018-06-08 | 0
9 | Help Desk Reply (Failure Transaction ) | 2018-06-11 | 2018-06-11 | 2018-06-11 | 0
10 | Added Register page and its related changes on FRA module. | 2018-06-11 | 2018-06-11 | 2018-06-11 | 0
11 | Added validation on registration page on VFPMC module | 2018-06-11 | 2018-06-11 | 2018-06-11 | 0
12 | Implemented the functionality of attachment in Registration page | 2018-06-12 | 2018-06-12 | 2018-06-12 | 0
13 | Fixed Permission NOC before not working with Kiosk User | 2018-06-13 | 2018-06-13 | 2018-06-13 | 0
14 | Insert New Naka Name in database as per excel sheet provided by client. | 2018-06-14 | 2018-06-14 | 2018-06-14 | 0
15 | Added the functionality to add multiple member inside grid along with DB work in JFMC module. | 2018-06-15 | 2018-06-15 | 2018-06-15 | 0
16 | Updated changes in FRA module | 2018-06-18 | 2018-06-18 | 2018-06-18 | 0
17 | Add radio button for vehicle Released/ Vehicle not released option below "Material Released/ Not Released " | 2018-06-20 | 2018-06-20 | 2018-06-20 | 0
18 | Added new functionality of Edit for Registration page from where they can modify their details in JFMC module. | 2018-06-22 | 2018-06-25 | 2018-06-22 | 3
19 | Mapped New (sikar) Users in Enchorochment Module | 2018-06-22 | 2018-06-22 | 2018-06-22 | 0
20 | Mapped new Assigner Users for amrita devi module | 2018-06-22 | 2018-06-22 | 2018-06-22 | 0
21 | Help Desk Reply(Want to know about advane tickt booking ) | 2018-06-26 | 2018-06-26 | 2018-06-26 | 0
22 | Worked on Fixed Amrita devi module bugs | 2018-06-28 | 2018-07-02 | 2018-06-28 | 4
1 | Updated Changes in Nursery Module | 2018-07-03 | 2018-07-04 | 2018-07-03 | 1
2 | Resolve the issue of Nursery Module | 2018-07-05 | 2018-07-05 | 2018-07-05 | 0
3 | Help Desk query resolve for refund | 2018-07-09 | 2018-07-09 | 2018-07-09 | 0
4 | Update the changing in FRA Module | 2018-07-10 | 2018-07-12 | 2018-07-12 | 0
5 | New Report created for Nursery | 2018-07-11 | 2018-07-13 | 2018-07-13 | 0
6 | Updated Education and Research Permit | 2018-07-12 | 2018-07-13 | 2018-07-13 | 0
7 | Created User registration form in FRA module | 2018-07-13 | 2018-07-16 | 2018-07-16 | 0
8 | Mapping of Naka as per client requirement | 2018-07-13 | 2018-07-13 | 2018-07-13 | 0
9 | Help Desk Query resolved | 2018-07-16 | 2018-07-16 | 2018-07-16 | 0
10 | Created Patch OF Nursery module and depolyed on production | 2018-07-17 | 2018-07-17 | 2018-07-17 | 0
11 | Created Report For FRA | 2018-07-18 | 2018-07-20 | 2018-07-20 | 0
12 | Convert the HTML Code into pdf in FRA | 2018-07-19 | 2018-07-20 | 2018-07-19 | 1
13 | Updated Animal Rescue Module | 2018-07-20 | 2018-07-23 | 2018-07-23 | 0
14 | Working on Education and Research Module | 2018-07-21 | 2018-07-21 | 2018-07-21 | 0
15 | Help Desk query asking for park reopen date | 2018-07-23 | 2018-07-23 | 2018-07-23 | 0
16 | Create New page for Education and Research wildlife | 2018-07-23 | 2018-07-26 | 2018-07-26 | 0
17 | Added new page for listing page in VFPMC page. | 2018-07-26 | 2018-07-30 | 2018-07-30 | 0
18 | Made the all changes in Claim request one time page as per new changes made in claim request page. | 2018-07-28 | 2018-07-30 | 2018-07-30 | 0
19 | Testing of Mobile application(Animal Rescue) | 2018-07-31 | 2018-07-31 | 2018-07-31 | 0
20 | Help desk query reply resolve issue | 2018-08-02 | 2018-08-02 | 2018-08-02 | 0
21 | Resolve the issue of Online Ticket booking | 2018-08-03 | 2018-08-03 | 2018-08-03 | 0
22 | Reolve query regarding refund | 2018-08-06 | 2018-08-06 | 2018-08-06 | 0
23 | Added the functionality of multiselection dropdown for Research Category and Wildlife Schedule | 2018-08-06 | 2018-08-07 | 2018-08-07 | 0
24 | Added grid for "Specimen / sample collection Details" entry in wildlife schedule | 2018-08-06 | 2018-08-09 | 2018-08-07 | 2
25 | Made changes on all the approver pages as per new changes made on Citizen part. | 2018-08-07 | 2018-08-07 | 2018-08-07 | 0
26 | Create a master for placeinventory | 2018-08-08 | 2018-08-13 | 2018-08-13 | 0
27 | Create a Master HeadRequiredForEmitraService | 2018-08-09 | 2018-08-13 | 2018-08-13 | 0
28 | Resolve the Query of help desk | 2018-08-10 | 2018-08-10 | 2018-08-10 | 0
29 | Create master of NP_ Place Kiosk User Mapping | 2018-08-13 | 2018-08-16 | 2018-08-16 | 0
30 | Map user of depot in pre-production server. | 2018-08-14 | 2018-08-14 | 2018-08-14 | 0
31 | Implemented the functionalities of Mail & sms notification to next level approver and to the requester who has raised the request. | 2018-08-16 | 2018-08-20 | 2018-08-20 | 0
32 | Fixed the issue of Claim request where citezen was unable to make request if they are approver users. | 2018-08-21 | 2018-08-23 | 2018-08-23 | 0
33 | Asking refund for failure transaction | 2018-08-23 | 2018-08-23 | 2018-08-23 | 0
34 | CWLW Dashboard | 2018-08-24 | 2018-08-28 | 2018-08-28 | 0
35 | Displayed Total Research request raised by Citizen, Displayed the bifurcation of Research request by Research Type in popup,Displayed the bifurcation of Research request by Research Type in popup. . | 2018-08-25 | 2018-08-27 | 2018-08-27 | 0
36 | FRA module-Provided Demo to Forest department team. | 2018-08-27 | 2018-08-27 | 2018-08-27 | 0
37 | Update Offence Module | 2018-08-28 | 2018-08-30 | 2018-08-30 | 0
38 | Displayed Total Rescue request raised by Citizen and Displayed the bifurcation of Rescue request by District in popup. Displayed the list of Rescue request in popup against selected District in dashboard | 2018-08-29 | 2018-09-01 | 2018-08-31 | 1
39

## March-May18 (hidden)
Service Level Agreement
Invoice Number |  | Month | Mar-May | Year | 2018
Resource Name | Megha pareek , Trishla Pareek | Work Order No | F4.3 (145)/RISL/TECH/15/6029 dt 28 Oct 2016 | Work Order Date | 2018-05-31
Sr.No. | Task Assigned | Assigned Date | Assign Task Completion Date | Actual Task Completion Date | Difference*
1 | Create SP and get SSO ID with Office ID | 2018-03-02 | 2018-03-05 | 2018-03-06 | 1
2 | Fixed the issue of view in manage notice page along with database work. | 2018-03-05 | 2018-03-09 | 2018-03-09 | 0
3 | Added addtional options in transit permit page for transport mode like Truck, Mini truck & Tracter and then worked on validation against transport mode selection. | 2018-03-08 | 2018-03-12 | 2018-03-12 | 0
4 | Map sso ID on prodcution | 2018-03-08 | 2018-03-12 | 2018-03-12 | 0
5 | Fixed Rescue module bugs with mobile team | 2018-03-09 | 2018-03-13 | 2018-03-13 | 0
5 | Create New Screen and import the excel file in Budget Allocation | 2018-03-12 | 2018-03-15 | 2018-03-15 | 0
6 | Hathi Gaon Live with kiosk user on Production | 2018-03-15 | 2018-03-17 | 2018-03-17 | 0
7 | Fixed bug in rescue module | 2018-03-15 | 2018-03-17 | 2018-03-15 | 2
8 | Check Rescue Mobile APP and API on live with mobile developer | 2018-03-19 | 2018-03-23 | 2018-03-23 | 0
9 | Implemented Kiosk User on Nahargarh ticketing on Staging | 2018-03-26 | 2018-03-26 | 2018-03-26 | 0
10 | Change Division Code in NOC report | 2018-03-27 | 2018-03-30 | 2018-03-30 | 0
11 | Fixed Elephant Module Bugs on Production | 2018-03-28 | 2018-04-02 | 2018-04-02 | 0
1 | Implement Budget Perposal new changes | 2018-04-02 | 2018-04-04 | 2018-04-04 | 0
1 | Resolve Pre Producation bugs | 2018-04-04 | 2018-04-11 | 2018-04-09 | 2
2 | Emitra Integration on counter booking | 2018-04-05 | 2018-04-06 | 2018-04-06 | 0
3 | created new scheme page in Budget Module | 2018-04-05 | 2018-04-06 | 2018-04-06 | 0
4 | New Citizen Dashboard Create Script and UI | 2018-04-07 | 2018-04-12 | 2018-04-12 | 0
6 | Created Window application for SLA and maintain log and upload on production | 2018-04-16 | 2018-04-16 | 2018-04-16 | 0
7 | Marge DOD module and check payment gateway on staging | 2018-04-16 | 2018-04-20 | 2018-04-19 | 1
8 | New Dashboard Module for FMDSS | 2018-04-18 | 2018-04-22 | 2018-04-21 | 1
9 | Created repository in SVN | 2018-04-19 | 2018-04-23 | 2018-04-22 | 1
10 | Change Budget Scheme Page | 2018-04-20 | 2018-04-20 | 2018-04-20 | 0
11 | Scheme modules changes upload on staging | 2018-04-20 | 2018-04-20 | 2018-04-20 | 0
12 | Nahargard print issue resolve | 2018-04-21 | 2018-04-23 | 2018-04-23 | 0
13 | Resolve query at FMDSS helpdesk | 2018-04-23 | 2018-04-23 | 2018-04-23 | 0
14 | Division Wise Citizen Permissions Status report transfer KT to Department User | 2018-04-24 | 2018-04-25 | 2018-04-25 | 0
15 | Help Desk Mail Reply | 2018-04-25 | 2018-04-25 | 2018-04-25 | 0
16 | Created patch of Jhalana booking report changes. | 2018-04-25 | 2018-04-26 | 2018-04-26 | 0
17 | Help Desk Mail Reply for Refund | 2018-04-28 | 2018-04-28 | 2018-04-28 | 0
18 | Load testing on fmdss | 2018-04-28 | 2018-04-28 | 2018-04-28 | 0
19 | Create Pre Survey Module in budget module | 2018-04-28
1 | Check FMDSS Revenue Summary Report not working properly | 2018-05-01 | 2018-05-04 | 2018-05-04 | 0
2 | Mapped id to FMDSS | 2018-05-02 | 2018-05-02 | 2018-05-02 | 0
3 | Create Excel sheet and count total no of Online booking with Indian and non Indian wise and same as counter booking | 2018-05-02 | 2018-05-04 | 2018-05-02 | 2
4 | Implemented upload option in all approver page where each approver has the option of upload . | 2018-05-02 | 2018-05-04 | 2018-05-03 | 1
5 | Remove Scheme Type Column in scheme master | 2018-05-03 | 2018-05-03 | 2018-05-03 | 0
6 | Create Online Summary Report on Production | 2018-05-04 | 2018-05-04 | 2018-05-04 | 0
7 | Create Pre Survey Budget Page For Range Level | 2018-05-06 | 2018-05-07 | 2018-05-07 | 0
8 | Check Why online booking not working on staging Environment | 2018-05-06 | 2018-05-06 | 2018-05-06 | 0
9 | Create Pre Survey Budget Page For Division Level | 2018-05-07 | 2018-05-09 | 2018-05-08 | 1
10 | Help Desk Reply for query for timming | 2018-05-08 | 2018-05-08 | 2018-05-08 | 0
11 | Create Pre Survey API in Budget Module Division level | 2018-05-09 | 2018-05-09 | 2018-05-09 | 0
12 | Pre Survey API Range Level and division level upload on Staging Server | 2018-05-10 | 2018-05-10 | 2018-05-10 | 0
13 | AddOffenceDetails page in protection module | 2018-05-11 | 2018-05-14 | 2018-05-14 | 0
14 | Design an Structure of database of protection Module | 2018-05-14 | 2018-05-16 | 2018-05-16 | 0
15 | Create Patch DOD module | 2018-05-15 | 2018-05-16 | 2018-05-16 | 0
16 | Create offence details page. | 2018-05-15 | 2018-05-16 | 2018-05-16 | 0
17 | Change some division name in budget module dashboard | 2018-05-16 | 2018-05-18 | 2018-05-16 | 2
18 | Add Two Head in Nursery Module and check reflection and resolve Nursery In-charge and citizen module | 2018-05-17 | 2018-05-18 | 2018-05-18 | 0
19 | Move all nursery report on staging server | 2018-05-21 | 2018-05-21 | 2018-05-21 | 0
20 | Added new page named "OffenceReport" under MISProtection. | 2018-05-21 | 2018-05-22 | 2018-05-21 | 1
21 | FMDSS Help Desk Mail Reply | 2018-05-21 | 2018-05-21 | 2018-05-21 | 0
22 | Create Nursery Report With Hindi Format | 2018-05-22 | 2018-05-22 | 2018-05-22 | 0
23 | Added the functionality of "Update Status" in show details page. | 2018-05-22 | 2018-05-24 | 2018-05-22 | 2
25 | Created Patch of Protection Module and then updated it on 179 server and production server, and then performed testing for the same. | 2018-05-22 | 2018-05-24 | 2018-05-22 | 2
26 | Added task details column in AddOffenceDetails and made changes on related page and procedure. | 2018-05-22 | 2018-05-25 | 2018-05-23 | 2
27 | Check Reviewer approver according to request ID | 2018-05-23 | 2018-05-24 | 2018-05-24 | 0
28 | Added the functionality of "Update Status" in show details page. | 2018-05-24 | 2018-05-24 | 2018-05-24 | 0
29 | Created New Pages for Department User Purchase Plants | 2018-05-26 | 2018-05-28 | 2018-05-28 | 0
30 | Performed testing on production. | 2018-05-29 | 2018-05-29 | 2018-05-29 | 0
31 | Added offence category field and made required changes on procedures and related pages. | 2018-05-30 | 2018-05-30 | 2018-05-30 | 0
32 | Update functionality for offence and applied validation. | 2018-05-31 | 2018-06-02 | 2018-05-31 | 2
Formulas:
Year = [Month]+4
Mar-May = [Year]+0

## Nov-jan2 (hidden)
Service Level Agreement
Invoice Number |  | Month | Nov-Jan | Year | 2017-2018
Resource Name | Arvind Sharma, Rajveer Sharma | Work Order No | F4.3(145)/RISL/TECH/15/3289 dated 15 Aug 2018 | Work Order Date | 2017-11-17
Sr.No. | Task Assigned | Assigned Date | Assign Task Completion Date | Actual Task Completion Date | Difference*
1 | Testing on Budget Estimation Module | 2017-11-01 | 2017-11-09 | 2017-11-07 | 2
2 | Resolve error On Pre Production Server | 2017-11-07 | 2017-11-13 | 2017-11-13 | 0
3 | Resolve error On Budget Estimation Module | 2017-11-07 | 2017-11-15 | 2017-11-13 | 2
1 | Helpdesk Mail Reply | 2017-11-09 | 2017-11-13 | 2017-11-13 | 0
2 | Resolve error On Pre Production Server | 2017-11-09 | 2017-11-15 | 2017-11-13 | 0
3 | Training for elephant module | 2017-11-11 | 2017-11-17 | 2017-11-15 | 2
4 | FRA module DB changes | 2017-11-15 | 2017-11-19 | 2017-11-19 | 0
1 | Refund process initiated | 2017-12-04 | 2017-12-08 | 2017-12-08 | 0
2 | Booking query (Help desk) | 2017-12-15 | 2017-12-19 | 2017-12-19 | 0
3 | mapped id to sso | 2017-12-26 | 2017-12-28 | 2017-12-28 | 0
4 | mapped id to sso | 2017-12-26 | 2017-12-28 | 2017-12-28 | 0
1 | Cancellation Request | 2018-01-01 | 2018-01-05 | 2018-01-05 | 0
2 | Refund process initiated | 2018-01-11 | 2018-01-16 | 2018-01-16 | 0
3 | E-sign help mannual created | 2018-01-18 | 2018-01-25 | 2018-01-25 | 0
1 | Mapping of request id to protection module | 2018-02-05 | 2018-02-07 | 2018-02-07 | 0
2 | Mapping SSO ID for FMDSS | 2018-02-07 | 2018-02-09 | 2018-02-09 | 0
3 | FMDSS Reply for refund | 2018-02-07 | 2018-02-14 | 2018-02-12 | 2
Formulas:
Nov-Jan = [Year]+2
Year = [Month]+4

## Nov-jan (hidden)
Service Level Agreement
Invoice Number |  | Month | Nov-Jan | Year | 2017-18
Resource Name | Arvind Sharma, Rajveer Sharma | Work Order No | F4.3(145)/RISL/TECH/15/3289 dated 15 Aug 2018 | Work Order Date | 2018-01-31
Sr.No. | Task Assigned | Assigned Date | Assign Task Completion Date | Actual Task Completion Date | Difference*
1 | Time Estimation for jhalana safari added in wildlife ticket booking and also in E-mitra | 2017-11-03 | 2017-11-06 | 2017-11-06 | 0
2 | Test Records of RTR booking in Production server | 2017-11-03 | 2017-11-06 | 2017-11-06 | 0
3 | New RSRC resources for FMDSS created | 2017-11-09 | 2017-11-16 | 2017-11-15 | 1
1 | Drawn KML for the NOC | 2017-12-22 | 2017-12-29 | 2017-12-29 | 0
2 | FRA Module Updated | 2017-12-29 | 2018-01-05 | 2018-01-03 | 2
1 | Drawn KML for the NOC | 2018-01-03 | 2018-01-10 | 2018-01-08 | 2
2 | FRA Module URL tested | 2018-01-25 | 2018-02-01 | 2018-01-30 | 2
3 | New Budget Report created | 2018-01-29 | 2018-02-05 | 2018-02-03 | 2
4 | Raj E-Sign service | 2018-01-30 | 2018-02-06 | 2018-02-04 | 2
5 | Reconcilation of all forest Transaction during New E-mitra | 2018-01-30 | 2018-02-06 | 2018-02-04 | 0
6 | Jaipur Zoo Booking Error resolved | 2018-01-30 | 2018-02-06 | 2018-02-04 | 0
7 | Added new sheet to FMDSS Dashboard for budget module | 2018-01-31 | 2018-02-07 | 2018-02-05 | 0
8 | Gis page error(Production server) | 2018-01-31 | 2018-02-07 | 2018-02-05 | 0
Formulas:
Nov-Jan = [Year]+2
Year = [Month]+5

## 15Feb to 14 May
Service Level Agreement
Invoice Number |  | Month | Nov-Jan | Year | 2017-2018
Resource Name | Ritu Sharma,kushal chauhan | Work Order No | F4.3 (145)/RISL/TECH/15/6029 dated 28 Oct 2016 | Work Order Date | 2018-05-14
Sr.No. | Task Assigned | Assigned Date | Assign Task Completion Date | Actual Task Completion Date | Difference*
1 | Resolve query at FMDSS helpdesk | 2018-02-15 | 2018-02-19 | 2018-02-19 | 0
2 | mapped id to sso | 2018-02-20 | 2018-02-23 | 2018-02-23 | 0
1 | Cancellation Request | 2018-03-08 | 2018-03-12 | 2018-03-12 | 0
2 | Refund process initiated | 2018-03-09 | 2018-03-13 | 2018-03-13 | 0
3 | E-sign help mannual created | 2018-03-16 | 2018-03-16 | 2018-03-16 | 0
1 | Implement Changes for Production Server | 2018-04-04 | 2018-04-11 | 2018-04-09 | 2
4 | Mapping of SSO ID with FMDSS | 2018-04-05 | 2018-04-06 | 2018-04-06 | 0
6 | Payment refund Process from Emitra | 2018-04-07 | 2018-04-12 | 2018-04-12 | 0
8 | Presentation On FMDSS | 2018-04-20 | 2018-04-23 | 2018-04-23 | 0
1 | Map sso ID on prodcution | 2018-05-08 | 2018-05-08 | 2018-05-08 | 0
2 | Fixed Rescue module bugs with mobile team | 2018-05-09 | 2018-05-09 | 2018-05-09 | 0
3 | FMDSS Mail reply | 2018-05-10 | 2018-05-10 | 2018-05-10 | 0
4 | Resolve Query Of citizen | 2018-05-11 | 2018-05-14 | 2018-05-14 | 0
Formulas:
Year = [Month]+4
Nov-Jan = [Year]+2

## 15Nov-14Feb
Service Level Agreement
Invoice Number |  | Month | Nov-Jan | Year | 2018
Resource Name | Ritu Sharma,kushal chauhan | Work Order No | F4.3 (145)/RISL/TECH/15/6029 dated 28 Oct 2016 | Work Order Date | 14/2/2018
Sr.No. | Task Assigned | Assigned Date | Assign Task Completion Date | Actual Task Completion Date | Difference*
1 | Training for elephant module | 2017-11-15 | 2017-11-17 | 2017-11-17 | 1
2 | FRA module DB changes | 2017-11-20 | 2017-11-23 | 2017-11-23 | 0
1 | Refund process initiated | 2017-12-04 | 2017-12-08 | 2017-12-08 | 0
2 | Booking query (Help desk) | 2017-12-15 | 2017-12-19 | 2017-12-19 | 0
3 | mapped id to sso | 2017-12-26 | 2017-12-28 | 2017-12-28 | 0
4 | mapped id to sso | 2017-12-26 | 2017-12-28 | 2017-12-28 | 0
1 | Cancellation Request | 2018-01-01 | 2018-01-05 | 2018-01-05 | 0
2 | Refund process initiated | 2018-01-11 | 2018-01-16 | 2018-01-16 | 0
3 | E-sign help mannual created | 2018-01-18 | 2018-01-25 | 2018-01-25 | 0
1 | Implement Changes for Production Server | 2018-02-02 | 2018-02-09 | 2018-02-07 | 2
4 | Mapping of SSO ID with FMDSS | 2018-02-05 | 2018-02-07 | 2018-02-07 | 0
6 | Payment refund Process from Emitra | 2018-02-12 | 2018-02-14 | 2018-02-14 | 0
8 | Presentation On FMDSS | 2018-02-12 | 2018-02-14 | 2018-02-14 | 0
Formulas:
Year = [Month]+4

## feb-April (hidden)
Service Level Agreement
Invoice Number |  | Month | Dec-Feb | Year | 2018
Resource Name | , Rajveer Sharma | Work Order No | F4.3(145)/RISL/TECH/15/3289 dated 15 Aug 2018 | Work Order Date | 2018-04-28
Sr.No. | Task Assigned | Assigned Date | Assign Task Completion Date | Actual Task Completion Date | Difference*
1 | Noc mining services online/kiosk user | 2018-02-01 | 2018-02-08 | 2018-02-06 | 0
2 | Resolved NOC Kiosk User not working on Production issue | 2018-02-01 | 2018-02-09 | 2018-02-06 | 3
3 | Mapping of request id to protection module | 2018-02-05 | 2018-02-07 | 2018-02-07 | 0
4 | Mapping SSO ID for FMDSS | 2018-02-07 | 2018-02-14 | 2018-02-12 | 2
5 | Division wise mapping in FMDSS Budget module | 2018-02-07 | 2018-02-12 | 2018-02-09 | 3
6 | FMDSS Service Issue resolved | 2018-02-08 | 2018-02-13 | 2018-02-10 | 3
7 | API for Kiosk transaction cancellation is done | 2018-02-08 | 2018-02-11 | 2018-02-11 | 0
8 | Revised Noc mannual | 2018-02-09 | 2018-02-24 | 2018-02-21 | 3
9 | KML request is completed | 2018-02-09 | 2018-02-14 | 2018-02-14 | 0
10 | Updated SSO ID for Fmdss | 2018-02-09 | 2018-02-13 | 2018-02-12 | 1
11 | Mapping Officers FMDSS Module with Additional charge officers | 2018-02-11 | 2018-02-18 | 2018-02-15 | 3
12 | Resolved Error in reports of revenue FMDSS | 2018-02-12 | 2018-02-19 | 2018-02-16 | 3
13 | SSO ID updation in FMDSS | 2018-02-12 | 2018-02-20 | 2018-02-18 | 2
14 | FMDSS New Deployment Diagram with Load balancer | 2018-02-15 | 2018-02-22 | 2018-02-19 | 3
15 | Update Draft for EESL proposal | 2018-02-15 | 2018-02-22 | 2018-02-19 | 3
16 | Budget Module updated | 2018-02-16 | 2018-02-23 | 2018-02-20 | 3
17 | Revised issue resolved | 2018-02-16 | 2018-02-23 | 2018-02-20 | 3
18 | FMDSS Service Issue resolved | 2018-02-16 | 2018-02-23 | 2018-02-20 | 3
19 | Mapped SSO ID to Fmdss | 2018-02-19 | 2018-02-26 | 2018-02-23 | 3
20 | Replacing SSO ID DCF,WL,jodhpur in FMDSS Module | 2018-02-19 | 2018-02-26 | 2018-02-23 | 3
1 | Create SP and get SSO ID with Office ID | 2018-03-02 | 2018-03-05 | 2018-03-06 | 1
2 | Fixed the issue of view in manage notice page along with database work. | 2018-03-05 | 2018-03-09 | 2018-03-09 | 0
3 | Added addtional options in transit permit page for transport mode like Truck, Mini truck & Tracter and then worked on validation against transport mode selection. | 2018-03-08 | 2018-03-12 | 2018-03-12 | 0
4 | Map sso ID on prodcution | 2018-03-08 | 2018-03-12 | 2018-03-12 | 0
5 | Fixed Rescue module bugs with mobile team | 2018-03-09 | 2018-03-13 | 2018-03-13 | 0
5 | Create New Screen and import the excel file in Budget Allocation | 2018-03-12 | 2018-03-15 | 2018-03-15 | 0
6 | Hathi Gaon Live with kiosk user on Production | 2018-03-15 | 2018-03-17 | 2018-03-17 | 0
7 | Fixed bug in rescue module | 2018-03-15 | 2018-03-17 | 2018-03-15 | 2
8 | Check Rescue Mobile APP and API on live with mobile developer | 2018-03-19 | 2018-03-23 | 2018-03-23 | 0
9 | Implemented Kiosk User on Nahargarh ticketing on Staging | 2018-03-26 | 2018-03-26 | 2018-03-26 | 0
10 | Change Division Code in NOC report | 2018-03-27 | 2018-03-30 | 2018-03-30 | 0
11 | Fixed Elephant Module Bugs on Production | 2018-03-28 | 2018-04-02 | 2018-04-02 | 0
1 | Implement Budget Perposal new changes | 2018-04-02 | 2018-04-04 | 2018-04-04 | 0
1 | Resolve Pre Producation bugs | 2018-04-04 | 2018-04-11 | 2018-04-09 | 2
2 | Emitra Integration on counter booking | 2018-04-05 | 2018-04-06 | 2018-04-06 | 0
3 | created new scheme page in Budget Module | 2018-04-05 | 2018-04-06 | 2018-04-06 | 0
4 | New Citizen Dashboard Create Script and UI | 2018-04-07 | 2018-04-12 | 2018-04-12 | 0
6 | Created Window application for SLA and maintain log and upload on production | 2018-04-16 | 2018-04-16 | 2018-04-16 | 0
7 | Marge DOD module and check payment gateway on staging | 2018-04-16 | 2018-04-20 | 2018-04-19 | 1
8 | New Dashboard Module for FMDSS | 2018-04-18 | 2018-04-22 | 2018-04-21 | 1
9 | Created repository in SVN | 2018-04-19 | 2018-04-23 | 2018-04-22 | 1
10 | Change Budget Scheme Page | 2018-04-20 | 2018-04-20 | 2018-04-20 | 0
11 | Scheme modules changes upload on staging | 2018-04-20 | 2018-04-20 | 2018-04-20 | 0
12 | Nahargard print issue resolve | 2018-04-21 | 2018-04-23 | 2018-04-23 | 0
13 | Resolve query at FMDSS helpdesk | 2018-04-23 | 2018-04-23 | 2018-04-23 | 0
14 | Division Wise Citizen Permissions Status report transfer KT to Department User | 2018-04-24 | 2018-04-25 | 2018-04-25 | 0
15 | Help Desk Mail Reply | 2018-04-25 | 2018-04-25 | 2018-04-25 | 0
16 | Created patch of Jhalana booking report changes. | 2018-04-25 | 2018-04-26 | 2018-04-26 | 0
17 | Help Desk Mail Reply for Refund | 2018-04-28 | 2018-04-28 | 2018-04-28 | 0
18 | Load testing on fmdss | 2018-04-28 | 2018-04-28 | 2018-04-28 | 0
Formulas:
Dec-Feb = [Year]+2
Year = [Month]+5