## Trishla Daily Status
S.NO | Date | FMDSS PROJECT | Status
1 | 2019-05-30 | Resolve Query of client by call/E-mail | DONE
2 | 2019-05-30 | Working on New Desgin of FMDSS application | Working
3 | 2019-05-30 | Map Forest User to FMDSS application | DONE
4 | 2019-05-30 | Check Daily Online Booking Reports | DONE
5 | 2019-05-30 | Working on Online Booking Report | DONE
6 | 2019-05-30 | Resolve Query of FRA team (Udaipur) through call | DONE
7 | 2019-05-30 | Provide Demo to FRA Collector office (Bhilwara) | DONE
S.NO | Date | FMDSS PROJECT | Status
1 | 2019-05-31 | Resolve Query of client by call/E-mail | Working
2 | 2019-05-31 | Working on New Desgin of FMDSS application | Working
3 | 2019-05-31 | Update and create user manuals | pending
4 | 2019-05-31 | Check Daily Online Booking Reports | DONE
5 | 2019-05-31 | Resolve issue and query of fra team updated issue | Working