## Issue log_updated
FRA ISSUES
S. No. | Issue Description as reported by TAD Team | User Role | FRA Team Status | TAD Team Remark | Issue reported on | Issue completed Date | Priority Level | Status
1 | In view survey details -> add option to view KML file on Map which is uploaded by gramsabha (At each level) | Gram Sabha | In Progress | KML Link visible but not showing on map | 2019-03-13 | 2019-06-07 | High | GIS related Issue(For test need SSO ID and password of gramsabha user )
2 | When we use Draw area on map, Map is not loading properly | Gram Sabha | pending | Pending | 2019-05-23 | 2019-06-07 | High | GIS related Issue(For test need SSO ID and password of gramsabha user )
4 | We need a specific dashboard for reviewing information easily.Use charts to graphically present information (As like Pie chart, line chart and bar chart). In FRA Portal we can use information like FRA claim summery (Pending Count, in-progress Count, Approved count etc), Claim intimation information on dashboard. | All | In Progress | pending | 2019-05-28 | 2019-06-07 | medium | Working
5 | Claim Request Summary report - > the summary report should include district wise filter so that only those name appear those district is selected .(like district Udaipur is selected form dropdown then only details of Udaipur appears ) | TAD | pending | not working | 2019-03-13 | 2019-06-07 |  | For admin level user ,required district wise drop down
6 | When we select individual in claim type then profile not working. | Citizen/Gram Sabha | In Progress | In Progress | 2019-03-13 | 2019-06-07 | medium | Design Related Issue
7 | remove navigation RTR Booking, and add tad department contact information on footer part as http://tad.rajasthan.gov.in/content/raj/tad/hi/home.html | All | pending |  | 2019-03-13 | 2019-06-07 | medium | Dashboard related issue
8 | Application popup is not in proper way and please check the all popup in the application. | All | pending |  | 2019-03-13 | 2019-06-07 | Low | Working
9 | We need intimation (SMS,Email) at every level after forwarding of application | All | pending | pending | 2019-05-28 | 2019-06-07 | High | Working
10 | Add Appeal option in FRA application ( If claimant is not satisfied with the decision, He can always appeal to higher authorities. As of now this option is not available in the application. Kindly add this feature on priority basis.) | All | pending | pending | 2019-06-07 |  | Very high | Working
14 | Gram sabha reject case should be show at SDO level reports | All | pending | pending | 2019-06-07 |  | medium | Working
15 | Add other option in drop down menu of rejection reason .After seleting other option then text display and user will enter other reason in text box. | All | pending | pending | 2019-06-07 |  | medium | Working
16 | SSO VALIDATION IN MAPPING PaGE | All | pending | pending | 2019-06-07 |  | medium | Working
17 | CHANGE NAME OF PREVIOUSLY DISPOSED TO APPROVED CASES AND HIDE APPROVAL GRID | All | pending | pending | 2019-06-07 |  | medium | Working
19 | FRA Application form should be in hindi and english | All | pending | pending | 2019-06-07 |  | medium | Working
20 | Need to add block and district drop down in both reports and fra role mapping page | All | pending | pending | 2019-06-07 |  | medium | Working
21 | Add option to display- for which level application is pending: i) Revenue level ii) Forest level iii) Gramsabha level | Old | Pending | pending | 2019-06-07 |  | medium
22 | Block Not showing on Claim Request Report | NEW | Pending | pending | 2019-06-11 |  | medium
23 | we Require status wise and Pending at level filtered report at each level user | NEW | Pending | pending | 2019-06-11 |  | medium
24 | FRA user mapping list not showing properly how can we check which user mapped or not | NEW | Pending | pending | 2019-06-11 |  | medium
26 | we required to Export mapped user list in Excel | NEW | Pending | pending | 2019-06-11 |  | medium
27 | We need one mapping page for fra mapping | New | Pending | pending | 2019-06-11 |  | medium
28 | Report Excel file is not in proper format: (in header not display department name, date etc.) and name of sheet not mentioned. Final Summary report should be in PDF as well as excel format in proper format just like below image (pending) | Old |  | Pending (Department name, report name, report type, from date and two date not showing on both excel and pdf) | 2019-06-11 |  | medium

## Issue
GIS Related Issue
FRA issue
Dashboard related design issue
Design Issue
Completed

## Issue
FRA ISSUES
| S. No. | Issue Description as reported by TAD Team | User Role | FRA Team Status | Tad Remark | Issue reported on
3 | 1 | while we are doing Mapping of Range Officer, we are able to select multiple blocks as well as multiple Grampanchayt. However, once a Grampanchayt is selected for an range officer it should not be visible to other range officer for selection. Though the system is showing all the grampanchayt to each and every range officer, whethar it is already mapped with another Range Officer. And Also Remove the Village option from edit user screen while doing Mapping of Range Officer. | Collector | Completed and deployed on Production Already | Not Working | 2019-05-25 | map
15 | 2 | FRA Application should also be in Hindi language because many uses use Hindi language. | All Users | In Progress | Not Working | 2019-03-13 | design
5 | 3 | At each level, the pending applications in the level below should be seen. At this point, this visibility is only there at the district level login. | All Users | In Progress | Not Working | 2019-03-13 | map
14 | 4 | Khasra No should be optional (this is not mandatory require) | Gram Sabha | Completed and deployed on Production Already | Not complie still have asked for land details. | 2019-03-13
13 | 5 | Add option to display- for which level application is pending: i) Revenue level ii) Forest level iii) Gramsabha level | All Users | Completed and deployed on Production Already | Not Working | 2019-03-13
| 6 | "In citizen: field repeat [Menu Item is repeating " | Citizen | Closed | not working | 2019-03-13 | design
| 7 | Report Excel file is not in proper format: (in header not display department name, date etc.) and name of sheet not mentioned. | All Users | Completed and deployed on Production Already | not working | 2019-03-13 | report
6 | 8 | Fra registration->Add new user->Role column: don’t display higher level in lower level (when login from TAD user then collector and TAD not shown) (Priority: High) | Collector | Completed and deployed on Production Already | not working | 2019-03-13 | map
7 | 9 | Need a filter and column of Designation, District and block that display user from there designation, District and block (like we select POT from the filter it will display all POT what are register and some record sso id and name not showing and require a delete button to remove user | Collector | Closed | Not Working | 2019-05-25 | map
| 10 | When we select individual in claim type then profile not working. | Citizen/Gram Sabha | In Progress | In Progress | 2019-03-13 | design
1 | 11 | In view survey details -> add option to view KML file on Map which is uploaded by gramsabha (At each level) | Gram Sabha | In Progress | In Progress | 2019-03-13 | kml
8 | 12 | Provision to update SSO IDs in case of Transfer of any User | All Users | In Progress | not working | 2019-05-25 | map
| 13 | Add application view button to view full application details on report and request details form | All Users | Closed | Not Working we just want to view whole application after single click with print function | 2019-03-13 | report
9 | 14 | Role and district dropdown bind as per permission (when login from TAD-Udaipur the only Udaipur district display in district dropdown box). | TAD | pending | not working | 2019-05-25 | map
| 15 | Final Summary report should be in PDF as well as excel format in proper format just like below image (pending) | TAD | Done | Not working | 2019-03-13 | report
| 16 | Claim Request Summary report - > the summary report should include district wise filter so that only those name appear those district is selected .(like district Udaipur is selected form dropdown then only details of Udaipur appears ) | TAD | pending | not working | 2019-03-13 | report
| 17 | Remove test application |  | pending | not working | 2019-03-13 | issue
| 19 | Change application name as tribal area development department |  | pending | not working | 2019-03-13 | design
| 20 | remove navigation RTR Booking, and add tad department contact information on footer part as http://tad.rajasthan.gov.in/content/raj/tad/hi/home.html |  |  |  | 2019-03-13 | design
| 21 | When we use Draw area on map, Map is not loading properly | Gram Sabha | pending | Pending | 2019-05-23 | kml
2 | 22 | After submitted latitude and longitude information than following alert occur. | Gram Sabha | pending | Pending | 2019-05-23 | kml
| 23 | E-sign Check box not showing on first record. | All | pending | Pending | 2019-05-23 | design
12 | 24 | When generate patwari halka and forest report without land information following alert are shown | Gram Sabha | pending | Pending | 2019-03-13
| 25 | Application popup is not in proper way and please check the all popup in the application. | All |  |  | 2019-03-13 | design
10 | 26 | When we enter SSO id on Previously Disposed claim Approver Actions part it occur following error ” Please enter valid SSO ID” | Gram Sabha | pending | Pending | 2019-05-28 | map
| 28 | We need intimation (SMS,Email) at every level after forwarding of application | All | pending | pending | 2019-05-28 | last
| 29 | On request details form Also have Search box upon the list so user can search the report data using (Claim Request ID, Date on Which, Claimant Name, Claim Type, Mobile Number, Khasra No, Status, Pending At). | All | pending | pending | 2019-05-28 | report
| 30 | We need a specific dashboard for reviewing information easily.Use charts to graphically present information (As like Pie chart, line chart and bar chart). In FRA Portal we can use information like FRA claim summery (Pending Count, in-progress Count, Approved count etc), Claim intimation information on dashboard. | All | pending | pending | 2019-05-28 | dash
11 | 31 | We need to upload our previous FRA claim to new portal but FRA team requires SSO-Id of Applicant and all approver. What is the need of SSO id for previous claims to be uploaded? | All | pending | pending | 2019-05-28 | claim

## Sheet1 (2)
FRA ISSUES
S. No. | Issue Description as reported by TAD Team | User Role | FRA Team Status | TAD Team Remark | Issue reported on | Issue completed Date | Status
1 | In view survey details -> add option to view KML file on Map which is uploaded by gramsabha (At each level) | Gram Sabha | In Progress | KML Link visible but not showing on map | 2019-03-13 | 2019-06-07 | Completed and deployed on Production
2 | When we use Draw area on map, Map is not loading properly | Gram Sabha | pending | Pending | 2019-05-23 | 2019-06-07 | Completed and deployed on Production
3 | while we are doing Mapping of Range Officer, we are able to select multiple blocks as well as multiple Grampanchayt. However, once a Grampanchayt is selected for an range officer it should not be visible to other range officer for selection. Though the system is showing all the grampanchayt to each and every range officer, whethar it is already mapped with another Range Officer. And Also Remove the Village option from edit user screen while doing Mapping of Range Officer. | Collector | Completed and deployed on Production Already | Not Working | 2019-05-25 | 2019-06-07 | Completed and deployed on Production
4 | At each level, the pending applications in the level below should be seen. At this point, this visibility is only there at the district level login. | All Users | In Progress | Not Working | 2019-03-13 | 2019-06-07 | Completed and deployed on Production
5 | Fra registration->Add new user->Role column: don’t display higher level in lower level (when login from TAD user then collector and TAD not shown) (Priority: High) | Collector | Completed and deployed on Production Already | not working | 2019-03-13 | 2019-06-07 | Completed and deployed on Production
6 | Need a filter and column of Designation, District and block that display user from there designation, District and block (like we select POT from the filter it will display all POT what are register and some record sso id and name not showing and require a delete button to remove user | Collector | Completed and deployed on Production Already | not working | 2019-03-13 | 2019-06-07 | Completed and deployed on Production
7 | Provision to update SSO IDs in case of Transfer of any User | All Users | In Progress | not working | 2019-05-25 | 2019-06-07 | Completed and deployed on Production
8 | Role and district dropdown bind as per permission (when login from TAD-Udaipur the only Udaipur district display in district dropdown box). | TAD |  | not working | 2019-05-25 | 2019-06-07 | Completed and deployed on Production
9 | When we enter SSO id on Previously Disposed claim Approver Actions part it occur following error ” Please enter valid SSO ID” | Gram Sabha | Done | Pending | 2019-05-28 | 2019-06-07 | In this case user who will fill the form will enter his/her sso id
10 | We need a specific dashboard for reviewing information easily.Use charts to graphically present information (As like Pie chart, line chart and bar chart). In FRA Portal we can use information like FRA claim summery (Pending Count, in-progress Count, Approved count etc), Claim intimation information on dashboard. | All | In Progress | pending | 2019-05-28 | 2019-06-07 | Working
11 | We need to upload our previous FRA claim to new portal but FRA team requires SSO-Id of Applicant and all approver. What is the need of SSO id for previous claims to be uploaded? | All | pending | pending | 2019-05-28 | 2019-06-07 | In this case user who will fill the form will enter his/her sso id
12 | Khasra No should be optional (it should not be mandatory) | Gram Sabha | Completed and deployed on Production Already | Not complie still have asked for land details. | 2019-03-13 | 2019-06-07 | Already deployed on Production
13 | Add option to display- for which level application is pending: i) Revenue level ii) Forest level iii) Gramsabha level | All Users | Completed and deployed on Production Already | Not Working | 2019-03-13 | 2019-06-07 | Completed and deployed on Production
14 | When generate patwari halka and forest report without land information following alert are shown | Gram Sabha | pending | Pending | 2019-03-13 | 2019-06-07 | Mandatory to fill mandatory field (land information)
15 | Report Excel file is not in proper format: (in header not display department name, date etc.) and name of sheet not mentioned. | All Users | Completed and deployed on Production Already | not working | 2019-03-13 | 2019-06-07 | Completed and deployed on Production
16 | Add application view button to view full application details on report and request details form | All Users | Closed | Not Working we just want to view whole application after single click with print function | 2019-03-13 | 2019-06-07 | Completed and deployed on Production
17 | Claim Request Summary report - > the summary report should include district wise filter so that only those name appear those district is selected .(like district Udaipur is selected form dropdown then only details of Udaipur appears ) | TAD | pending | not working | 2019-03-13 | 2019-06-07 | Report already filter as district wise
18 | On request details form Also have Search box upon the list so user can search the report data using (Claim Request ID, Date on Which, Claimant Name, Claim Type, Mobile Number, Khasra No, Status, Pending At). | All | pending | pending | 2019-05-28 | 2019-06-07 | Closed (Already have)
19 | FRA Application should also be in Hindi language because many users use Hindi language. | All Users | In Progress | Not Working | 2019-03-13 | 2019-06-07 | Working
20 | "In citizen: field repeat [Menu Item is repeating " | Citizen | Closed | not working | 2019-03-13 | 2019-06-07 | Completed and deployed on Production
21 | When we select individual in claim type then profile not working. | Citizen/Gram Sabha | In Progress | In Progress | 2019-03-13 | 2019-06-07 | working
22 | Change application name as tribal area development department |  | pending | not working | 2019-03-13 | 2019-06-07 | Completed and deployed on Production
23 | remove navigation RTR Booking, and add tad department contact information on footer part as http://tad.rajasthan.gov.in/content/raj/tad/hi/home.html | All | pending |  | 2019-03-13 | 2019-06-07 | working
24 | E-sign Check box not showing on first record. | All |  |  | 2019-05-23 | 2019-06-07 | closed
25 | Application popup is not in proper way and please check the all popup in the application. | All |  |  | 2019-03-13 | 2019-06-07 | working
26 | Remove test application |  | pending | not working | 2019-03-13 | 2019-06-07 | Already Done
27 | We need intimation (SMS,Email) at every level after forwarding of application | All | Done | pending | 2019-05-28 | 2019-06-07 | Completed and deployed on Production