## Issue
FRA ISSUES
S. No. | Issue Description as reported by TAD Team | User Role | FRA Team Status | Tad Remark | Issue reported on
1 | while we are doing Mapping of Range Officer, we are able to select multiple blocks as well as multiple Grampanchayt. However, once a Grampanchayt is selected for an range officer it should not be visible to other range officer for selection. Though the system is showing all the grampanchayt to each and every range officer, whethar it is already mapped with another Range Officer. And Also Remove the Village option from edit user screen while doing Mapping of Range Officer. | Collector | Completed | Not Working | 2019-05-25
2 | FRA Application should also be in Hindi language because many uses use Hindi language. | All Users | Not related to work flow | Not Working | 2019-03-13
3 | At each level, the pending applications in the level below should be seen. At this point, this visibility is only there at the district level login. | All Users |  | Not Working | 2019-03-13
4 | Khasra No should be optional (this is not mandatory require) | Gram Sabha | Completed and deployed on Production Already | Not complie still have asked for land details. | 2019-03-13
5 | Add option to display- for which level application is pending: i) Revenue level ii) Forest level iii) Gramsabha level | All Users | Completed and deployed on Production | Not Working | 2019-03-13
6 | "In citizen: field repeat (Priority: High) [Menu Item is repeating -screenshot provided]" | Citizen | Closed | not working | 2019-03-13
7 | Report Excel file is not in proper format: (in header not display department name, date etc.) and name of sheet not mentioned. | All Users | Completed and deployed on Production | not working | 2019-03-13
8 | Fra registration->Add new user->Role column: don’t display higher level in lower level (when login from TAD user then collector and TAD not shown) (Priority: High) | Collector | Completed and deployed on Production | not working | 2019-03-13
9 | 10) Need a filter and column of Designation, District and block that display user from there designation, District and block (like we select POT from the filter it will display all POT what are register and some record sso id and name not showing and require a delete button to remove user | Collector | Completed and deployed on Production ( not added delete button) | Not Working | 2019-05-25
10 | When we select individual in claim type then profile not working. | Citizen/Gram Sabha | Not related to work flow | In Progress | 2019-03-13
11 | 11) In view survey details -> add option to view KML file on Map which is uploaded by gramsabha | Gram Sabha | Completed and deployed on Production | In Progress | 2019-03-13
12 | 12) Provision to update SSO IDs in case of Transfer of any User | All Users | closed (User can deactivated the sso id and add new sso id in case of transfer ) | not working | 2019-05-25
13 | 13) Add application view button to view full application details on report and request details form | All Users | Completed and deployed on Production Added View button without print functionality | Not Working we just want to view whole application after single click with print function | 2019-03-13
14 | Role and district dropdown bind as per permission (when login from TAD-Udaipur the only Udaipur district display in district dropdown box). | TAD | Completed and deployed on Production | not working | 2019-05-25
15 | Final Summary report should be in PDF as well as excel format in proper format just like below image (pending) | TAD | Completed and deployed on Production | Not working | 2019-03-13
16 | Claim Request Summary report - > the summary report should include district wise filter so that only those name appear those district is selected .(like district Udaipur is selected form dropdown then only details of Udaipur appears ) | TAD | Report already filter as per district mapped | not working | 2019-03-13
17 | Remove test application |  | closed | not working | 2019-03-13
18 | How to change old user to new |  | closed | not working | 2019-03-13
19 | Change application name as tribal area development department |  | Completed and deployed on Production | not working | 2019-03-13
20 | remove navigation RTR Booking, and add tad department contact information on footer part as http://tad.rajasthan.gov.in/content/raj/tad/hi/home.html |  |  |  | 2019-03-13
21 | When we use Draw area on map, Map is not loading properly | Gram Sabha | Completed and deployed on Production | Pending | 2019-05-23
22 | After submitted latitude and longitude information than following alert occur. | Gram Sabha | closed | Pending | 2019-05-23
23 | E-sign Check box not showing on first record. | All | closed | Pending | 2019-05-23
24 | When generate patwari halka and forest report without land information following alert are shown | Gram Sabha | closed (required to fill mandatory fields) | Pending | 2019-03-13
25 | Application popup is not in proper way and please check the all popup in the application. | All |  |  | 2019-03-13
26 | 26) When we enter SSO id on Previously Disposed claim Approver Actions part it occur following error ” Please enter valid SSO ID” | Gram Sabha | closed (User who entering previously disposed details will enter his/her sso id ) | Pending | 2019-05-28
27 | We need a specific dashboard for reviewing information easily. | All | working | pending | 2019-05-28
28 | We need intimation (SMS,Email) at every level after forwarding of application | All | Completed and deployed on Production | pending | 2019-05-28
29 | On request details form Also have Search box upon the list so user can search the report data using (Claim Request ID, Date on Which, Claimant Name, Claim Type, Mobile Number, Khasra No, Status, Pending At). | All | already have | pending | 2019-05-28
30 | Use charts to graphically present information (As like Pie chart, line chart and bar chart). In FRA Portal we can use information like FRA claim summery (Pending Count, in-progress Count, Approved count etc), Claim intimation information on dashboard. | All | working | pending | 2019-05-28
31 | We need to upload our previous FRA claim to new portal but FRA team requires SSO-Id of Applicant and all approver. What is the need of SSO id for previous claims to be uploaded? | All | Closed (User who entering the details in previous disposal form will enter his/her SSO Id in all the approval steps ) | pending | 2019-05-28